## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
TB KARYA ABADI
Toko Bangunan Karya Abadi |  |  |  |  | Legend: |  | On track |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Client : Adam Mahesa
Project start date: | 2024-10-28 | [6 empty] | October | [6 empty] | November | [27 empty] | December
Scrolling increment: | 0 | < Scroll / Bulan, INC 5 - 10 | time axis 2024-10-28 to 2024-12-22
Tasks | Category | Assigned to | Progress | Start | Days | Milestone | time axis 2024-10-28 to 2024-12-22
Kebutuhan Client
Membuat Pertanyaan Client | On Track | Analyst | 100% | 2024-10-28 | 2 | Menghasilkan daftar pertanyaan
Wawancara Client | On Track | Analyst | 100% | 2024-10-30 | 1 | Mendapatkan informasi atau jawaban dari pertanyaan yang telah disiapkan
Analisis Biaya yang Dibutuhkan | On Track | Analyst | 75% | 2024-10-31 | 1 | Mendapatkan gambaran biaya yang dikeluarkan dalam pengerjaan proyek
Identifikasi Client | On Track | Analyst | 50% | 2024-11-01 | 2 | Memperdalam permintaan fitur dan desain sesuai keinginan client
Inisiasi Rancangan UI/UX | On Track | Analyst, Designer | 50% | 2024-11-03 | 1 | Menghasilkan rancangan menggunakan media tulis
Rancangan UI/UX
Rancangan Mockup | High Risk | Designer | 0% | 2024-11-04 | 7
Perancangan Low Fidelity | On Track | Designer | 0% | 2024-11-11 | 3
Perancangan High Fidelity | Low Risk | Designer | 0% | 2024-11-14 | 3
Review Rancangan UI/UX Dengan Client | Low Risk | PM, Analyst, Designer | 0% | 2024-11-17 | 1
Front End
Pemrograman HTML | Med Risk | Programmer, PM | 0% | 2024-11-18 | 15
Pemrograman JS (JavaScript) | High Risk | Programmer, PM | 0% | 2024-11-18 | 15
Pemroraman CSS | Med Risk | Programmer, PM | 0% | 2024-11-18 | 15
Evaluasi Front End | Med Risk | Programmer, PM |  | 2024-12-04 | 2
Demo Testing | Med Risk | Tester, PM, Programmer |  | 2024-12-06 | 1
Back End
Pembuatan Database SQL | High Risk | Programmer, PM | 0% | 2024-12-07 | 15
Pembuatan API WhatsApp | High Risk | Programmer, PM | 0% | 2024-12-21 | 15
Pembuatan System Pembayaran | High Risk | Programmer, PM | 0% | 2025-01-05 | 15
Testing Dan Evaluasi | Milestone | Tester, PM, Programmer | 0% | 2025-01-20 | 3
Testing Dan Evaluasi
Final Testing | Goal |  |  | 2025-01-23 | 5
Dokumentasi | On Track |  | 10% | 2024-10-28 | 92
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT: Dark
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Gupreet Bawa
Project start date: | 2024-11-04 |  |  |  |  | November | [27 empty] | December
Scrolling increment: | 5 | time axis 2024-11-09 to 2025-01-03
Milestone description | Category | Assigned to | Progress | Start | Days | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
TITLE 1
Task 1 | Goal | Name | 25% | 2024-11-04 | 3
Task 2 | Milestone |  |  | 2024-11-09 | 1 | bar: S
Task 3 | Low Risk |  | 50% | 2024-11-01 | 10
Task 4 | Milestone |  |  | 2024-11-24 | 1 | bar: S
Task 5 | Med Risk |  | 10% | 2024-11-10 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-11-10 | 13
Task 2 | On Track |  | 50% | 2024-11-12 | 9
Task 3 | Low Risk |  | 33% | 2024-11-17 | 11
Task 4 | Milestone |  |  | 2024-11-19 | 1 | bar: T
Task 5 |  |  |  | 2024-11-20 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-11-19 | 4
Task 2 | Med Risk |  |  | 2024-11-22 | 14
Task 3 | On Track |  |  | 2024-12-07 | 6
Task 4 | Goal |  |  | 2024-12-11 | 3 | W: 2; T: 2; F: 2
Task 5 | Low Risk |  |  | 2024-11-10 | 19
TITLE 4
Task 1 |  |  |  | 2024-12-14 | 15
Task 2 |  |  |  | 2024-12-28 | 5
Task 3 | Milestone |  |  | 2025-02-08 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT: Color
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Hayden Cook
Project start date: | 2024-11-04 |  |  |  |  | November | [27 empty] | December
Scrolling increment: | 5 | time axis 2024-11-09 to 2025-01-03
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-11-09 to 2025-01-03
TITLE 1
Task 1 | Goal | Name | 25% | 2024-11-04 | 3
Task 2 | Milestone |  |  | 2024-11-09 | 1 | bar: 2024-11-09
Task 3 | Low Risk |  | 50% | 2024-11-01 | 10
Task 4 | Milestone |  |  | 2024-11-24 | 1 | bar: 2024-11-24
Task 5 | Med Risk |  | 10% | 2024-11-10 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-11-10 | 13
Task 2 | On Track |  | 50% | 2024-11-12 | 9
Task 3 | Low Risk |  | 33% | 2024-11-17 | 11
Task 4 | Milestone |  |  | 2024-11-19 | 1 | bar: 2024-11-19
Task 5 |  |  |  | 2024-11-20 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-11-19 | 4
Task 2 | Med Risk |  |  | 2024-11-22 | 14
Task 3 | On Track |  |  | 2024-12-07 | 6
Task 4 | Goal |  |  | 2024-12-11 | 3 | 2024-12-11: 2; 2024-12-12: 2; 2024-12-13: 2
Task 5 | Low Risk |  |  | 2024-11-10 | 19
TITLE 4
Task 1 |  |  |  | 2024-12-14 | 15
Task 2 |  |  |  | 2024-12-28 | 5
Task 3 | Milestone |  |  | 2025-02-08 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one